## Overview
Threat Identification, Analysis and Risk Assessment (TIARA) Project Delivery Plan
Company Name | ABC Company
Document Name | Threat Identification, Analysis and Risk Assessment (TIARA) Delivery Plan
Document ID | TRA-01-01-01
Version | 1
Date | 2020-03-26
Created By | XXXX
Reviewed By | XXXX

## Gantt Chart
TIARA Service Project Schedule
ABC Company
| Project Start Date | 2020-03-20 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Jeffrey Lee | [6 empty] | 2020-03-16 | [6 empty] | 2020-03-23 | [6 empty] | 2020-03-30 | [6 empty] | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04
 | time axis 2020-03-16 to 2020-05-10
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2020-03-16 to 2020-05-10
1 | Kick Off Meeting |  |  |  | - |  |  | -
1.1 | Define service scope, service content and delivery plan | XXX | XXX | 2020-03-20 | 2020-03-20 | 1 | 0% | 1
1.2 | Gather end user requirements | XXX | XXX | 2020-03-20 | 2020-03-20 | 1 | 0% | 1
1.3 | Confirm end user's network architecture | XXX | XXX | 2020-03-20 | 2020-03-20 | 1 | 0% | 1
2 | Service Components Mounting |  |  |  | - |  |  | -
2.1 | Mount service components | XXX | XXX | 2020-03-24 | 2020-03-24 | 1 | 0% | 1
2.2 | Configure the settings of components ensure connectivity in order | XXX | XXX | 2020-03-24 | 2020-03-24 | 1 | 0% | 1
2.3 | Verify licenses, serial number, policies and rule base are in order | XXX | XXX | 2020-03-24 | 2020-03-24 | 1 | 0% | 1
2.4 | Fine tuning service to ensure no false positives | XXX | XXX | 2020-03-27 | 2020-03-27 | 1 | 0% | 1
3 | Threat Monitoring and Analysis Service |  |  |  | - |  |  | -
3.1 | Network threat monitoring and analysis | XXX | XXX | 2020-03-24 | 2020-04-06 | 14 | 0% | 10
3.2 | Onsite deep threat analysis | XXX | XXX | 2020-04-06 | 2020-04-08 | 3 | 0% | 3
3.3 | Onsite security event diagnosis | XXX | XXX | 2020-04-06 | 2020-04-08 | 3 | 0% | 3
3.4 | Technical discussion | XXX | XXX | 2020-04-09 | 2020-04-09 | 1 | 0% | 1
4 | Executives Presentation |  |  |  | - |  |  | -
4.1 | Report preparation | XXX | XXX | 2020-04-10 | 2020-04-15 | 6 | 0% | 4
4.2 | Business Impact Analysis (BIA) | XXX | XXX | 2020-04-10 | 2020-04-10 | 1 | 0% | 1
4.3 | Gap analysis | XXX | XXX | 2020-04-13 | 2020-04-13 | 1 | 0% | 1
4.4 | Long term improvement plan recommendation | XXX | XXX | 2020-04-14 | 2020-04-14 | 1 | 0% | 1
4.5 | Executives presentation slides preparation | XXX | XXX | 2020-04-15 | 2020-04-15 | 1 | 0% | 1
5 | Project Closure |  |  |  | - |  |  | -
5.1 | Service components unmounting | XXX | XXX | 2020-04-16 | 2020-04-16 | 1 | 0% | 1
-
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Delivery Plan
Week | Activity | Service Content | Lead | Predecessor | Start Date | End Date
1 | Kick Off Meeting | Define service scope, service content and delivery plan | XXX | XXX | 2020-03-20 | 2020-03-20
1 |  | Gather end user requirements | XXX | XXX | 2020-03-20 | 2020-03-20
1 |  | Confirm end user's network architecture | XXX | XXX | 2020-03-20 | 2020-03-20
1 | Service Components Mounting | Mount service components | XXX | XXX | 2020-03-24 | 2020-03-24
1 |  | Configure the settings of components ensure connectivity in order | XXX | XXX | 2020-03-24 | 2020-03-24
1 |  | Verify licenses, serial number, policies and rule base are in order | XXX | XXX | 2020-03-24 | 2020-03-24
1 |  | Fine tuning service to ensure no false positives | XXX | XXX | 2020-03-27 | 2020-03-27
1 - 3 | Threat Monitoring and Analysis Service | Network threat monitoring and analysis | XXX | XXX | 2020-03-24 | 2020-04-06
3 |  | Onsite deep threat analysis | XXX | XXX | 2020-04-06 | 2020-04-08
3 |  | Onsite security event diagnosis | XXX | XXX | 2020-04-06 | 2020-04-08
3 |  | Technical discussion | XXX | XXX | 2020-04-09 | 2020-04-09
3 - 4 | Executives Presentation | Report preparation | XXX | XXX | 2020-04-10 | 2020-04-15
3 |  | Business Impact Analysis (BIA) | XXX | XXX | 2020-04-10 | 2020-04-10
4 |  | Gap analysis | XXX | XXX | 2020-04-13 | 2020-04-13
4 |  | Long term improvement plan recommendation | XXX | XXX | 2020-04-14 | 2020-04-14
4 |  | Executives presentation slides preparation | XXX | XXX | 2020-04-15 | 2020-04-15
4 | Project Closure | Service components unmounting | XXX | XXX | 2020-04-16 | 2020-04-16

## Service Scope
Service Scope | Service Contents
Malware Events | To identify the hidden malware within the internal network that might not be visible to security products and have lateral movement to other hosts Examples: Ransomware, mining virus, CnC communication, trojan
Attack Events | Analyze the network traffics that contain attack patterns that Examples: webshell attack, brute force attack, SQL injections
Vulnerability Events | Identify the vulnerabilities of applications and hosts that could affect the security status Examples: outdated / unsupported software version, unhardened service configurations
Abnormal Behavior Events | Identify the presense of insecure practices and network abnormalies before they turn into real security incidents. Examples: port scanning events, abnormal traffic behaviors
Protocol Audit | Identify the presence of insecure or high risk ports in the networks and perform the auditing on the protocols against industry best practices. Examples: SMB version 1, plain text ports such as HTTP or FTP